## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Saptarshi | 2025-09-30 | Data set is not helpful for direct model training | Sprint 1 | Backend Team | Maintainability | Dataset is again preprocessed using correlation between variables. | 2025-10-03 | Closed | Data is now prepared and useful in model training
2 | Vardhan | 2025-10-06 | Model had been collapsed, giving same output for any data | Sprint2 | Backend Team | Logical | Reconstructing model architecture and trains on different models | 2025-10-13 | Closed | Various models have been trained and picking one with accurate results.
3 | Kshitij | 2025-10-06 | LLM training issues due to lack of high computing GPUs | Sprint3 | Backend Team | Standards | Using Colab for training the model | 2025-10-20 | Closed | Not possible for training LLM. So we have tried SLM.
4 | Anjali | 2025-10-14 | Used XGBoost for fraud detection. But model is affected by overfitting. | Sprint4 | Backend Team | Logical | Regularization and Data Augmentation has been applied to overcome the overfitting | 2025-10-22 | Closed | XG Boost is giving better results compared to other models in efficient time.
5 | Sameer | 2025-10-24 | Deployment of XGBoost may be encountered to security issues and Dashboard should be added in User-Interface | Sprint 5 | Frontend Team | User Interface | Added login page and interactive dashboard in the app | 2025-10-31 | Closed | No issues in UI.
6 | Abhay Singh | 2025-10-31 | phi-3 slm has been fine tuned but accuracy is not satisfied and need to integrate in app | Sprint 6 | Both teams | Maintainability | SLM has been added in the app. | 2025-11-02 | Closed | Apart of SLM for better results we have used API keys for chtgpt.
7 | Megha | 2025-11-03 | SLM is taking more computing time and effecting system performance. | Sprint 7 | Backend Team | Standards | APIs have been replaced instead of SLM | 2025-11-06 | Closed | Api is working Properly.
8 | Chaitanya | 2025-11-07 | The developed Churn Prediction model has been trained on incorrect dataset. | Sprint 8 | Backend Team | Logical | Again trained the model with correct dataset. | 2025-11-10 | Closed | Model is integrated in the App.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others